## Project Description
Your Name: | BJ Paner
Project Description:
A 3D graphics application designed to emulate a Rubiks Cube rendered in a browser using HTML, Javascript, and the Three.js library. Ideally, the player will be able to manipulate distinct rows and columns of a 3D object as though it were the genuine article

## User Stories
User Stories
UserStory# | StoryName | As a … | I want… | So That… | Status
0 | Model | User | the cube to load in a solved state | I have something to interact with | Complete
1 | LeftMouse | User | to be able to rotate specific rows and columns with the left mouse button | I can play with the cube model | Incomplete
2 | RightMouse | User | to manipulate the rotation of the cube with the right mouse button | I can view my actions have affected the cube across the entire model | Complete
3 | Pivot | User | to have each subsection of the cube pivot around a specific shared origin point | interacting with the model resembles the genuine article | Complete
4 | Stickers | User | to have each subsection of the cube have it's own unique coloration | I can differentiate individual pieces as it the model is rotated | Complete
5 | Rotation | User | to have full 360 degree rotation across the X, Y, and Z axis | I can have access to a full view of the model at all times | Incomplete
6 | Reset | User | to be able to reset the face positions of the cube into a solved state | I can reset the cube if I can't solve it manually | Incomplete
7 | Borders | User | to have a bold border seperating each face | each "sticker" is more distinct and to make the model more realistic | Complete
8 | Exit | User | to be able to close the program | I can exit the program at any time | Undefined
9 | Solved | User | the program to recognize when the puzzle is in a solved state | I know when I have sucessfully solved the cube | Incomplete
10 | Shuffle | User | the cube to shuffle itself on command | I don't have to shuffle the cube myself | Incomplete
11 |  | User

## Backlog
Backlog |  |  | (Bug or Task)
Priority | BacklogId | StoryName | BacklogType | Description | In | InSprint | Status
10 | 1 | Rotation | Task | The cubes have been instantiated, but cannot rotate like a real Rubiks cube | index.html | Sprint 1 | Incomplete
8 | 2 | Pivot | Task | Each sub-section of the cube rotates around its own local origin, rather than that of the cube as a whole | index.html | Sprint 1 | Complete
6 | 3 | Orbit Control | Task | The camera control does not have full 360 degree rotation along the x-axis, only 180 | index.html | Sprint 1 | Incomplete
4 | 4 | Border | Bug | The borders between the faces of the "stickers" cannot change in thickness | index.html | Sprint 1 | Incomplete
2 | 5 | Code | Task | All unique code is contained in index.html, rather than a custom .js file | index.html | Sprint 1 | Incomplete

## Sprint1_11-19
Sprint 1
Points | BacklogId | StoryName | BacklogType | Description | In | Status
10 | 1 | Rotation | Task | The cubes have been instantiated, but cannot rotate like a real Rubiks cube | index.html | Incomplete
6 | 3 | Orbit Control | Task | The camera control does not have full 360 degree rotation along the x-axis, only 180 | index.html | Incomplete
4 | 4 | Border | Bug | The borders between the faces of the "stickers" cannot change in thickness | index.html | Incomplete
2 | 5 | Code | Task | All unique code is contained in index.html, rather than a custom .js file | index.html | Incomplete
8 | 2 | Pivot | Task | Each sub-section of the cube rotates around its own local origin, rather than that of the cube as a whole | index.html | Complete
Link to Branch: |  | https://github.com/bpaner21/Graphics_Apps_Final_Project/tree/Week_3
Notes from Review:

## Sprint2_11-26
Sprint 2
Points | BacklogId | StoryName | BacklogType | Description | In
10 | 1 | LoadModel | Bug |  | someClass.cs
3 | 3 | SeeInstructions
2 | 2 | LoadModel
4
Link to Branch:
Notes from Review:

## Sprint3_12-3
Sprint 3
Points | BacklogId | StoryName | BacklogType | Description | In
10 | 1 | LoadModel | Bug |  | someClass.cs
3 | 3 | SeeInstructions
2 | 2 | LoadModel
4
Link to Branch:
Notes from Review:

## Release
Release
Points | BacklogId | StoryName | BacklogType | Description | In
10 | 1 | LoadModel | Bug |  | someClass.cs
3 | 3 | SeeInstructions
2 | 2 | LoadModel
4
Link to Branch:
AFTER SHIPPING, REVIEW MAIN BACKLOG AND MARK STATUS
Notes from Review: